## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 19 | DAY 2 20 | DAY 3 21 | DAY 4 23 | DAY 5 24 | DAY 6 25 | DAY 7 26 | DAY 8 28 | DAY 9 29 | DAY 10 30 | DAY 11 1 | DAY 12 2 | SPRINT REVIEW
User Story 1 | 8
Database: maintenance activity and EWO tables | 2 | Antonietta Napoli | Completed | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement html interface to add, remove or modify and activity | 2 | Antonella Rossi | Completed | 3 | 3 | 3 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement php module to read maintenance data from db and create json file | 2 | Angelo Vistocco | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
Implement js class to manage data in the html file | 2 | Simona Sorgente | Completed | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 2 | 2
Database: data about maintenance activities | 2 | Simona Sorgente | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story 3 | 4
Implement an html interface to list all scheduled maintenance activities ordered by week | 1 | Antonella Rossi | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 0 | 0 | 0
Implement a php module to get data from DB | 2 | Angelo VIstocco | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0
Implement js module to show maintenance informations in the html | 1 | Antonietta Napoli | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0
User Story 4 | 4
HTML: show all the general information about scheduled maintenance activities | 1 | Antonella Rossi | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 0 | 0
implement a php module to get data from DB | 2 | Angelo Vistocco | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0
Implement a js module to show data in the html | 1 | Simona Sorgente | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
User Story 5 | 2
Implement js function to change the html view by pressing a button | 2 | Simona Sorgente | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 1 | 0
User Story 10 | 2
HTML: provide a blank workspace note to write information about the activity | 1 | Antonella Rossi | Completed | 1 | [9 empty] | 1 | 0.5 | 0 | 0 | bar: DAY 1 19 to DAY 9 29
Database: store information about the maintenance activity | 1 | Simona Sorgente | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
User Story 19-24 | 16
Database: list of competences related to a specific task | 2 | Antonietta Napoli | Completed | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database: manage sites, which are composed of factory site (branch offices) and area (or department) inside the factory | 1 | Simona Sorgente | Completed | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teams' Components | Total Story Points | Total Hours
Database: list of materials | 1 | Antonietta Napoli | Completed | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Antonietta Napoli | 9 | 11
Database: list of Maintenance procedures | 1 | Simona Sorgente | Completed | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Antonella Rossi | 9 | 12
PHP module to get data | 4 | Angelo Vistocco | Completed | 4 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | Simona Sorgente | 10 | 13
JS module to interact with HTML | 2 | Antonietta Napoli | Completed | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Angelo Vistocco | 10 | 13
Implement an HTML view for system admin to manage data in the DB | 4 | Antonella Rossi | Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
Database: maintenance typologies as Electrical, electronic, hydraulic, mechanical | 1 | Antonietta Napoli | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 38 |  |  | 49 | 43 | 42 | 37 | 30 | 28 | 25 | 22 | 19 | 16 | 12 | 7.5 | 3 | 0