## Agile Product Backlog
AGILE PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
|  | Sprint 1 | Angelo Vistocco | 2020-11-19 |  |  | Yes | High | Not Started | 38
US1 | Manage maintenance activities | " " | " " | 2020-11-23 | 2020-11-26 | Yes | Yes | High | Not Started | 8 | Yes | This section is for the drop-down list
US2 | Record maintenance data | " " | " " | 2020-11-19 | 2020-11-20 | Yes | Yes | High | Not Started | 2 | Yes | Yes | High | Complete
US3 | View scheduled maintenance activities list | " " | " " | 2020-11-26 | 2020-12-01 | Yes | Yes | High | Not Started | 4 | Yes | No | Medium | In Progress
US4 | View scheduled maintenance activities informations | " " | " " | 2020-11-26 | 2020-12-01 | Yes | Yes | Medium | Not Started | 4 | Yes
US5 | Create the link between the previous views | " " | " " | 2020-12-02 | 2020-12-02 | Yes | Yes | High | Not Started | 2 | Yes
US19-24 | Manage procedure maintenance data | " " | " " | 2020-11-19 | 2020-11-26 | No | Yes | High | Not Started | 16 | Yes
US10 | Make possible to insert workspace notes | " " | " " | 2020-11-26 | 2020-12-01 | Yes | Yes | Medium | Not Started | 2 | Yes
|  | Sprint 2 | Antonietta Napoli | 2020-12-03 |  |  | No | High | Not Started | 22 |  |  | Low | Not Started
US13-14 | Manage users and Maintainers competencies | " " | " " | 2020-12-03 | 2020-12-09 | No | No | High | Not Started | 8 | Yes
US6 | Select a Maintainer from a list of maintainers | " " | " " | 2020-12-09 | 2020-12-14 | Yes | No | High | Not Started | 4 | Yes
US7 | Select a time slot for the maintainer | " " | " " | 2020-12-15 | 2020-12-15 | Yes | No | High | Not Started | 2 | Yes
US9 | Send a notification to the selected Maintainer and to the Production manager | " " | " " | 2020-12-15 | 2020-12-16 | Yes | No | High | Not Started | 4 | Yes
US8 | View for selected activity and selected maintainer | " " | " " | 2020-12-09 | 2020-12-14 | Yes | No | Medium | Not Started | 4 | Yes
|  | Sprint 3 | Antonella Rossi | 2020-12-17 |  |  | No |  | Not Started | 32
US12 | View list of assigned tickets (EWO) | " " | " " | 2020-12-17 | 2020-12-22 | Yes | No | Medium | Not Started | 4 | Yes
US15 | Associate to a Maintainer the procedure to be performed according to each maintenance activity. | " " | " " | 2020-12-17 | 2020-12-22 | Yes | No | High | Not Started | 4 | Yes
US16 | Associate to a Maintenance Procedure a Standard Maintenance Procedure (SMP) file in PDF format. | " " | " " | 2020-12-17 | 2020-12-22 | Yes | No | Medium | Not Started | 4 | Yes
US18 | Record ot the application accesses | " " | " " | 2020-12-17 | 2020-12-29 | Yes | No | High | Not Started | 8 | Yes
US25 | Select a Maintainer for an EWO activity | " " | " " | 2020-12-28 | 2020-12-30 | Yes | No | High | Not Started | 4 | Yes
US26 | Send a notification to the Maintainer who has an EWO activity and to the Production manager | " " | " " | 2020-12-30 | 2020-12-30 | Yes | No | High | Not Started | 4 | Yes
U11 | Manage materials needed to run a maintenance activity. | " " | " " | 2020-12-17 | 2020-12-22 | Yes | No | Medium | Not Started | 4 | Yes