## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG WITH BURNDOWN CHART - SPRINT 2
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1: 5 | DAY 2: 7 | DAY 3: 9 | DAY 4: 10 | DAY 5: 11 | DAY 6: 12 | DAY 7: 14 | DAY 8: 15 | DAY 9: 16 | SPRINT REVIEW
User Story #13-14 | 8
Create system admin interface in html to assign skills to maintainers | 1 | Antonella Rossi | completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create system admin interface in html to manage users | 1 | Antonella Rossi | completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create html login interface for users like planner or maintainer | 1 | Antonella Rossi | completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement php module to assign skills to maintainers and its test cases | 1 | Angelo Vistocco | completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement php module to manage users and its test cases | 2 | Angelo Vistocco | completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement js module to populate html assigning skills interface | 1 | Antonietta Napoli | completed | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement js module to populate html managing users | 1 | Antonietta Napoli | completed | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #6 | 4
Create an html interface to select a maintainer among all the maintainers | 2 | Simona Sorgente | completed | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Implement a php module to load all maintainers and its test cases | 1 | Angelo Vistocco | completed | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Implement a js module to populate html with maintainers loaded with php module | 1 | Antonietta Napoli | completed | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
User Story #7 | 4
Create an html interface to show maintainer availability and to select a specific time slot for him | 1.5 | Antonella Rossi | completed | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0
Implement a php module to load time slots for a specific maintainer and its test cases | 1 | Angelo Vistocco | completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Implement a js module to populate html with maintainer time slots loaded with php module | 1 | Simona Sorgente | completed | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Get selected time slot in html with js | 0.5 | Antonietta Napoli | completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0
User Story #8 | 4
Create an html view to show the selected maintainer and the selected activity | 1.5 | Antonella Rossi | completed | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Implement a php module to load the selected maintainer and the selected activity | 1.5 | Angelo Vistocco | completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0
Implement a js module to populate html with selected maintainer and activity | 1 | Antonietta Napoli | completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
User Story #9 | 4
Implement js function to send notification to a maintainer | 1.5 | Simona Sorgente | completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Teams' Components | Total Story Points | Total Hours
Modify db in order to let a user add an e-mail address | 1 | Antonietta Napoli | completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Antonietta Napoli | 5.5 | 10
Implement js function to send notification to the production manager | 1.5 | Simona Sorgente | completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Antonella Rossi | 6 | 11
Integration test | [14 empty] | Simona Sorgente | 6 | 9
Test all the classes together |  | TEAM 5 | completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | Angelo Vistocco | 6.5 | 11
TOTAL |  |  |  | 41 | 39 | 33 | 25 | 22 | 20 | 16 | 12 | 4 | 0 | 0

## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 18 | 14